## Sheet1
9/2/2022 - Q2/3 Record of Revision TRM Filing
Detailed Work Plan
No. |  | Task | Estimated Completion Date | Effective Date in TRM | Comments
1 |  | File Q2 2022 ROR |  |  | To be filed by Orange and Rockland 9/22022
|  | New Measures |  |  | Work plan for Q2 2022 is an estimate of the work anticipated to be completed for the quarter. This list is subject to change based on TRM MC priorities and workload.
| RES | Heat Pump Clothes Dryer | 2022-09-02 | 2022-09-02
| RES | Connected Lighting | 2022-09-02 | 2022-09-02
Review of updates/questions within various measures
| RES | Refrigerator and Freezer | 2022-09-02 | 2023-01-01
| RES | Dehumidifier Recycling | 2022-09-02 | 2023-01-01
| RES | DHW Aquastat Turndown | 2022-09-02 | 2023-01-01 | Measure to be removed
| RES | Energy and Heat Recovery Ventilator | 2022-09-02 | 2023-01-01
| RES | Window | 2022-09-02 | 2023-01-01
| C&I | Variable Speed Drive Vacuum Pump - Dairy Farms | 2022-09-02 | 2023-01-01
| C&I | Compressed Air Low Pressure Drop Filters | 2022-09-02 | 2023-01-01
| C&I | Central Domestic Hot Water (DHW) Control | 2022-09-02 | 2023-01-01
| C&I | DHW Temperature Turndown | 2022-09-02 | 2023-01-01
| C&I | Energy and Heat Recovery Ventilator | 2022-09-02 | 2023-01-01
| C&I | Interior Lighting Control | 2022-09-02 | 2023-01-01
| C&I | Induction Cooktop | 2022-09-02 | 2023-01-01
| C&I | Heat Pump - Air Source | 2022-09-02 | 2023-01-01
| RES/C&I | Appendix P | 2022-09-02 | 2023-01-01
2 |  | File Q3/4 2022 ROR |  |  | To be filed by Orange and Rockland 6/30/2022
|  | New Measures |  |  | Work plan for Q3/4 2022 is an estimate of the work anticipated to be completed for the quarter. This list is subject to change based on TRM MC priorities and workload.
| C&I | Learning Thermostat | 2022-12-30 | 2022-12-30 | Originally proposed by Wildan in "Energy Management as a Service" measure. Measure developed by NYSERDA's RTEM team.
| C&I | Real Time Energy Management | 2022-12-30 | 2022-12-30 | Originally proposed by Wildan in "Energy Management as a Service" measure. Measure developed by NYSERDA's RTEM team. It will involve tiered-approach.
| C&I | Refrigeration Condenser Coil Cleaning | 2022-12-30 | 2022-12-30 | Submitted by CoilPod
| C&I | Smart Water Heater Control
Review of updates/questions within various measures
| RES | Refrigerator and Freezer | 2022-12-30 | 2024-01-01
| RES/C&I | Appendix Q | 2022-12-30 | 2024-01-01 | PLSF Table
|  | NY TRM Stakeholder Forum | TBD | TBD
3 |  | TRM Version 10 Filing | 2022-09-30 | 2023-01-01 | In response to codification of a 45 lm/W backstop requirement for general service lamps (GSLs), revisions will include adjustments to lighting baseling tables, lifetime benefits, and EULs. The response to the imposed GSL standard will be in the V10 NY TRM filing. To be filed by Con Ed 9/30/2022